## To-Do List
Hospital Management System (HMS) — 10-Week To-Do List
Set Status for each task as you complete it — Priority and Notes are editable.
Overall Progress: |  | 0 of 62 tasks done (0%)
Week | Phase | Task | Priority | Status | Notes
1 | Planning & Requirement Analysis | Study the problem domain and current hospital workflows | Medium | Not Started
1 | Planning & Requirement Analysis | Finalise functional requirements from the specification document | High | Not Started
1 | Planning & Requirement Analysis | Finalise non-functional requirements from the specification document | High | Not Started
1 | Planning & Requirement Analysis | Define project scope and objectives | High | Not Started
1 | Planning & Requirement Analysis | Set up project management board (Trello/Notion/GitHub Projects) | Medium | Not Started
1 | Planning & Requirement Analysis | Create GitHub repository and project structure | Medium | Not Started
2 | System Design | Design the 4-layer system architecture | High | Not Started
2 | System Design | Design the database schema / ERD for all modules | High | Not Started
2 | System Design | Create Figma wireframes for the dashboard | Medium | Not Started
2 | System Design | Create Figma wireframes for patient, appointment and billing screens | Medium | Not Started
2 | System Design | Review design with supervisor/mentor and revise | Medium | Not Started
3 | Environment Setup & User Management | Set up development environment (IDE, server, database) | High | Not Started
3 | Environment Setup & User Management | Configure Git/GitHub branching workflow | Medium | Not Started
3 | Environment Setup & User Management | Implement login and logout | High | Not Started
3 | Environment Setup & User Management | Implement password management | Medium | Not Started
3 | Environment Setup & User Management | Implement user roles and role-based access control | High | Not Started
3 | Environment Setup & User Management | Test the authentication module | Medium | Not Started
4 | Patient Management Module | Build patient registration form | High | Not Started
4 | Patient Management Module | Build update/edit patient information | Medium | Not Started
4 | Patient Management Module | Build search patient feature | Medium | Not Started
4 | Patient Management Module | Build view medical history feature | Medium | Not Started
4 | Patient Management Module | Build document upload feature | Low | Not Started
4 | Patient Management Module | Test the Patient Management module | Medium | Not Started
5 | Doctor & Appointment Management | Build doctor registration and profile screens | Medium | Not Started
5 | Doctor & Appointment Management | Build doctor schedule management | Medium | Not Started
5 | Doctor & Appointment Management | Build appointment booking | High | Not Started
5 | Doctor & Appointment Management | Build appointment cancel/reschedule | Medium | Not Started
5 | Doctor & Appointment Management | Build appointment status tracking | Medium | Not Started
5 | Doctor & Appointment Management | Test Doctor & Appointment modules | Medium | Not Started
6 | Electronic Medical Records & Laboratory | Build diagnosis entry screen | High | Not Started
6 | Electronic Medical Records & Laboratory | Build prescription entry screen | High | Not Started
6 | Electronic Medical Records & Laboratory | Build treatment history view | Medium | Not Started
6 | Electronic Medical Records & Laboratory | Build lab test request feature | Medium | Not Started
6 | Electronic Medical Records & Laboratory | Build sample tracking feature | Low | Not Started
6 | Electronic Medical Records & Laboratory | Build lab result entry and report generation | Medium | Not Started
6 | Electronic Medical Records & Laboratory | Test EMR & Laboratory modules | Medium | Not Started
7 | Pharmacy & Billing | Build medicine inventory management | High | Not Started
7 | Pharmacy & Billing | Build stock management | Medium | Not Started
7 | Pharmacy & Billing | Build expiry monitoring/alerts | Medium | Not Started
7 | Pharmacy & Billing | Build prescription processing (pharmacy side) | Medium | Not Started
7 | Pharmacy & Billing | Build billing and invoice generation | High | Not Started
7 | Pharmacy & Billing | Build payment recording | Medium | Not Started
7 | Pharmacy & Billing | Test Pharmacy & Billing modules | Medium | Not Started
8 | Staff Management & Reports | Build employee registration | Medium | Not Started
8 | Staff Management & Reports | Build attendance tracking | Medium | Not Started
8 | Staff Management & Reports | Build leave records | Low | Not Started
8 | Staff Management & Reports | Build dashboard with key metrics | High | Not Started
8 | Staff Management & Reports | Build reports (patient, revenue, pharmacy, lab, staff) | High | Not Started
8 | Staff Management & Reports | Test Staff Management & Reports modules | Medium | Not Started
9 | Integration, Testing & Security | Integrate all modules together | High | Not Started
9 | Integration, Testing & Security | Perform unit testing | High | Not Started
9 | Integration, Testing & Security | Perform integration testing | High | Not Started
9 | Integration, Testing & Security | Perform system testing | High | Not Started
9 | Integration, Testing & Security | Fix bugs identified during testing | High | Not Started
9 | Integration, Testing & Security | Apply security measures (encryption, session timeout, audit logs) | High | Not Started
9 | Integration, Testing & Security | Test backup and recovery | Medium | Not Started
10 | Deployment & Documentation | Deploy the system to server/hosting | High | Not Started
10 | Deployment & Documentation | Prepare user manual | Medium | Not Started
10 | Deployment & Documentation | Prepare technical documentation | Medium | Not Started
10 | Deployment & Documentation | Conduct user acceptance testing (UAT) | High | Not Started
10 | Deployment & Documentation | Prepare final presentation slides | Medium | Not Started
10 | Deployment & Documentation | Submit final project report | High | Not Started

## Weekly Progress
Weekly Progress Summary
Week | Total Tasks | Done | % Complete
1 | 6 | 0 | 0%
2 | 5 | 0 | 0%
3 | 6 | 0 | 0%
4 | 6 | 0 | 0%
5 | 6 | 0 | 0%
6 | 7 | 0 | 0%
7 | 7 | 0 | 0%
8 | 6 | 0 | 0%
9 | 7 | 0 | 0%
10 | 6 | 0 | 0%
Total | 62 | 0 | 0%